## Settings
key | value | description
schema_version | 2 | Do not change: canonical importer emits roadmap.v2.
title | Payments roadmap | Roadmap title.
time_scale | month | week ¦ month ¦ quarter ¦ date ¦ order
lane_dimension | product | Grouping dimension shown to readers.
shift_threshold_days | 3 | Absolute shift at or below this value is unchanged.
assumptions |  | Optional values separated by ¦.

## Lanes
id | title | description
checkout | Checkout | Checkout workstream

## Tasks
id | title | lane | start | end | start_order | end_order | status | owner | risk | milestones | outcomes | notes
task-wallets | Wallet support | checkout | 2026-07-01 | 2026-10-07 |  |  | at_risk | Payments | Risk of API delay | m-wallet-pilot | outcome-fast-payments

## MilestoneHistory
milestone_id | milestone_title | lane | revision_id | revision_order | plan_version | planned_date | planned_order | recorded_at | is_current | reason | status | owner | risk | outcomes | notes | previous_planned_date | shift_days | cumulative_shift_days | shift_state
m-wallet-pilot | Wallet pilot | checkout | rev-1 | 1 | 2026-05 | 2026-09-15 |  | 2026-05-10 | FALSE | Initial plan | planned | Payments |  | outcome-fast-payments
m-wallet-pilot | Wallet pilot | checkout | rev-2 | 2 | 2026-06 | 2026-09-30 |  | 2026-06-12 | FALSE | Billing API delay | at_risk | Payments |  | outcome-fast-payments
m-wallet-pilot | Wallet pilot | checkout | rev-3 | 3 | 2026-07 | 2026-10-14 |  | 2026-07-08 | FALSE | Retesting | blocked | Payments |  | outcome-fast-payments
m-wallet-pilot | Wallet pilot | checkout | rev-4 | 4 | 2026-08 | 2026-10-07 |  | 2026-08-03 | TRUE | Schedule optimized | on_track | Payments |  | outcome-fast-payments

## Dependencies
id | from | to | type | impact | rationale
dep-wallets | task-wallets | m-wallet-pilot | blocks | high | Build must finish before pilot

## Outcomes
id | title | description | metric
outcome-fast-payments | Faster successful payments | Reduce checkout time | Payment success rate

## Lists (hidden)
Statuses | DependencyTypes | Impacts | TimeScales | Booleans | ShiftStates
planned | blocks | low | week | TRUE | initial
in_progress | depends_on | medium | month | FALSE | unchanged
on_track | influences | high | quarter |  | delayed
at_risk | relates_to |  | date |  | accelerated
blocked |  |  | order
done
cancelled

## Instructions
Field | Meaning
previous_planned_date | Previous revision date for the same milestone_id.
shift_days | Current planned_date minus previous_planned_date.
cumulative_shift_days | Sum of sequential shifts from the first revision.
shift_state | initial / unchanged / delayed / accelerated using Settings.shift_threshold_days.
Purpose | Fill a working copy of this file. Never edit the bundled template inside the skill.
Required flow | Copy template -> fill/confirm -> import to roadmap.v2 YAML -> strict validate -> generate Draw.io -> source-aware validate.
Dates | Use ISO dates YYYY-MM-DD. Excel date cells are accepted and normalized.
Milestone history | One row per revision. Keep milestone_id stable, revision_id unique, revision_order strictly increasing, and exactly one is_current=TRUE.
Computed columns | Do not edit the four yellow columns. The importer ignores cached/formula results and recalculates all shifts from planned_date/planned_order.
Lists | Separate multiple milestone/outcome IDs with ¦. IDs must match ^[A-Za-z][A-Za-z0-9_-]*$.
Example | The four Wallet pilot revisions show +15d, +14d, -7d and +22d cumulative.
Security | Do not paste formulas or external links into input columns. This workbook contains no macros or external links.